## Sheet1
Test case ID | Description | Steps to reproduce | Expected Result | Status | Actual Result (If needed) | Priority | Env | Preconditions
tc_001 | validate the home button | 1.click on home in nav bar | home page must be open | pass | home page is opened successfully | high
tc_002 | validate refreshing the home page when clicking on categories button | 1.navigate to home 2.click on categories | new categories appear | pass | all categories appear successfully
tc_003 | validate phones category | 1.navigate to home 2.click on categories 3.click on phones | all phones must appear | pass | all phone products appear successfully
tc_004 | validate laptops category | 1.navigate to home 2.click on categories 3.click on laptops | all laptops must appear | pass | all laptop products appear successfully
tc_005 | validate monitors category | 1.navigate to home 2.click on categories 3.click on Monitors | all monitors must appear | pass | all monitor products appear successfully
tc_006 | validate each product info in phone category | 1.navigate to home 2.click on categories 3.click on phones 4.click on any product | name , image ,description ,price of the product appear | pass | all product info appear successfully
tc_007 | validate add to cart button in any product | 1.navigate to home 2.click on categories 3.click on phones 4.click on any product 5.click on add to cart | product must be added to cart | pass | product is added to cart successfully
tc_008 | validate carousel navigation "ads" | 1.navigate to home 2.click on next and previous arrows | previous and next must work | pass | next and previous photos appear successfully
tc_009 | validate previous button at end of home page in phone category | 1.navigate to home 2.click on phone category 3.scroll to the end of the page 3.click on previous button | all product of phone category only appears | fail | products of all catogory appear
tc_010 | validate footer appear in the end of home page | 1.navigate to home 2.scroll to the end of the page | all info of footer must appear | pass | footer appear successfully
tc_011 | validate about us button | 1.click on about us in nav bar | pop up message must appear | pass | pop up message appear successfully
tc_012 | validate "X" button in pop up message | 1.click on about us in nav bar 2.click on x button | pop up message must be closed | pass | pop up message closed successfully
tc_013 | validate close button in pop up message | 1.click on about us in nav bar 2.click on close button | pop up message is closed | pass | pop up message closed successfully
tc_014 | validate about us play video button | 1.click on about us in nav bar 2.click on play button | video must be opened and sound is played | pass | video is opened and sound is played successfully
tc_015 | validate pause video button | 1.click on about us in nav bar 2.click on play button 3.click on pause button | video must be paused | pass | video is paused successfully
tc_016 | validate minimzie and maximize screen button | 1.click on about us in nav bar 2.click on play button 3.click on full screen button 4. click on minimzie button | video with full screen must appear then the screen should be minimize | pass | full screen is opened successfully and minimized successfully
tc_017 | validate picture In picture button | 1.click on about us in nav bar 2.click on play button 3.click on picture in picture button | picture in picture must appear | pass | picture in picture appear successfully
tc_018 | validate sound button | 1.click on about us in nav bar 2.click on play button 3.click on sound button | user can mute, increase or decrease sound | pass | sound button is worked successfully
tc_019 | validate slider bar button | 1.click on about us in nav bar 2.click on play button 3.click slider button to
tc_020 | validate login with valid username and password | 1.navigate to login page 2.enter valid username and password 3.click on login button | login successfully and redirect to home page | pass |  | high
tc_021 | validate login with invalid username | 1.navigate to login page 2.enter any invalid username and valid password 3.click on login button | error message "user does not exist" | pass |  | high
tc_022 | validate login with empty username | 1.navigate to login page 2.enter valid password 3.click on login button | erorr message "please fill out username and password " | pass
tc_023 | validate login with spaces before or after username | 1.navigate to login page 2.enter spaces before username and valid password 3.click on login button | login successfully and trim spaces | fail | error message "user does not exist" | medium
tc_024 | validate login with case sensitive in username | 1.navigate to login page 2.enter valid username and password 3.click on login button | error message "user does not exist" | pass |  | medium
tc_025 | validate login attempt with browser back button | 1.navigate to login page 2.enter valid username and password 3.click on login button |  | pass
tc_026 | validate login with invalid password | 1.navigate to login page 2.enter valid username and invalid password 3.click on login button | error message "wrong password" | pass |  | high
tc_027 | validate login with empty password | 1.navigate to login page 2.enter valid username 3.click on login button | error message "please fill out username and password " | pass |  | medium
tc_028 | validate login with spaces before or after password and between | 1.navigate to login page 2.enter valid username and spaces before password 3.click on login button | error message "wrong password" | fail |  | medium
tc_029 | validate login with case sensitive in password | 1.navigate to login page 2.enter valid username and password 3.click on login button | error message "wrong password" | pass |  | medium
tc_030 | validate close button or x or outside | 1.navigate to login page 2.enter valid username and password 3.click on close button | login page closed | pass |  | low
tc_031 | validate logout button | 1.click on logout button | logout successfully and navigate to home page | pass |  | high |  | user is logged in
tc_032 | validate login with empty username and password | 1.navigate to login page 2.click login button | error message "please fill out username and password " | pass |  | low
tc_033 | validate show and hide password button | 1.navigate to login page 2.enter valid username and password 3.click on eye button | password should be hide or show | fail | does not appear usually | low
tc_034 | validate sending message with valid email and username, message | 1- navigate to home page 2.click on contact 3- enter valid email , username and message 4- click on sending message | notification appears to user "thanks for sending message | pass |  | low
tc_035 | validate sending message with invalid email form and valid name , message | 1- navigate to home page 2.click on contact 3- enter invalid email , valid username and message 4- click on sending message | error message "enter valid email " | fail | notification appears to user "thanks for sending message | low
tc_036 | validate sending message with empty email and valid name , message | 1- navigate to home page 2.click on contact 3- enter, valid username and message 4- click on sending message | error message "fill out email " | fail | notification appears to user "thanks for sending message | low
tc_037 | validate sending message with valid email and invalid name less than 2 letters, valid message | 1- navigate to home page 2.click on contact 3- enter, valid email, invalid name and valid message 4- click on sending message | error message "enter valid name " | fail | notification appears to user "thanks for sending message | low
tc_038 | validate sending message with valid email and invalid name more than 30 letters, valid message | 1- navigate to home page 2.click on contact 3- enter, valid email, invalid name and valid message 4- click on sending message | error message "enter valid name " | fail | notification appears to user "thanks for sending message | low
tc_039 | validate sending message with valid email and invalid name with special characters only, valid message | 1- navigate to home page 2.click on contact 3- enter, valid email, invalid name and valid message 4- click on sending message | error message "enter valid name " | fail | notification appears to user "thanks for sending message | low
tc_040 | validate sending message with valid email and invalid name with numbers only, valid message | 1- navigate to home page 2.click on contact 3- enter, valid email, invalid name and valid message 4- click on sending message | error message "enter valid name " | fail | notification appears to user "thanks for sending message | low
tc_041 | validate sending message with valid email and empty name with numbers only, valid message | 1- navigate to home page 2.click on contact 3- enter, valid email and valid message 4- click on sending message | error message "fill out name " | fail | notification appears to user "thanks for sending message | low
tc_042 | validate sending message with valid email and valid name , empty message | 1- navigate to home page 2.click on contact 3- enter valid emal, valid username and message 4- click on sending message | error message "fill out message " | fail | notification appears to user "thanks for sending message | low
tc_043 | validate sending message with valid email and valid name , invalid message less than 2 letters | 1- navigate to home page 2.click on contact 3- enter valid email, valid username and invalid message 4- click on sending message | error message "enter valid message " | fail | notification appears to user "thanks for sending message | low
tc_044 | validate sending message with valid email and valid name , valid message with 2 letters | 1- navigate to home page 2.click on contact 3- enter valid email, valid username and valid message 4- click on sending message | notification appears to user "thanks for sending message | pass |  | low
tc_045 | validate sending message with valid email and valid name , valid message with 100 letters | 1- navigate to home page 2.click on contact 3- enter valid email, valid username and valid message 4- click on sending message | notification appears to user "thanks for sending message | pass |  | low
tc_046 | validate sending message with valid email and valid name , invalid message with more than 100 letters | 1- navigate to home page 2.click on contact 3- enter valid email, valid username and invalid message 4- click on sending message | error message "enter valid message " | fail | notification appears to user "thanks for sending message | low
tc_047 | validate sending message with empty email ,name and message | 1- navigate to home page 2.click on contact 4- click on sending message | error message "fill out email, name and message" | fail | notification appears to user "thanks for sending message | low
tc_048 | validate home button | 1- click on home page | direct user to home page | pass |  | medium
tc_049 | validate the left and right scrolling of products in home page | 1.navigate to home page 2.scroll left 3.scroll right | The product should change to the next one for right scrolling The product should change to the previous one for left scrolling | pass |  | medium
tc_050 | validate that each product details page display the correct product information (name, price, description) | 1.navigate to home page 2.click on any product | the system should show the product info to use | pass |  | medium
tc_051 | validate visual search on each product | 1.navigate to home page 2.click on visual search of specific product | A page should appear to user contain searching for the same product | pass |  | low
tc_052 | Verify the 3 dots (setting )on each product | 1- navigate to home page 2. click on 3 dots on specific product | setting of this product should appear | pass |  | low
tc_053 | Verify that phone category displays only phone product | 1.navigate home page 2.click on phones button in category | only phone pages displayed | pass |  | medium
tc_054 | Verify that labtops category displays only phone product | 1.navigate home page 2.click on labtops button in category | only labtops pages displayed | pass |  | medium
tc_055 | Verify that monitors category displays only phone product | 1.navigate home page 2.click on monitors button in category | only monitors pages displayed | pass |  | medium
tc_056 | Verify that next and previous option in home page | 1.navigate to home page 2.click on next button 3.click on previous button | The page next to the one you are should appear The previous page should appear | pass |  | medium
tc_057
tc_058
tc_059
tc_060
tc_061
tc_062